## Sheet1
SMPG Investment Funds WG Action Items Status. Last updated 26 September 2016
# | Topic | Classification | Action | Responsible | Proposed Timing | Status | Status Date | Additional Information 1 | Additional Information 2
1 | Account Management MP (SR 2015 version) on MyStandards | ACMT | Update UGs and ‘process document’, upload to MyStandards, set to public | JEC | Q2 2015 | CLOSED | 20 April 2015. | SMPG-Global-IF-AccountManagement-Final (2015-04-20)
2 | Account Management maintenance 2016 | ACMT | Submit CR to ISO to add LEI to Individual Person and Organisation. Party Identification 2 Choice will need to be replaced by a component that allows a choice of BIC , Proprietary Identification, Name And Address and an optional LEI. | JEC | By 8 May For review in 19 May 2015 IF Monthly meeting | CLOSED |  | Reviewed in meeting 19 May 2015.
3 | Account Management maintenance 2016 | ACMT | CR to be submitted: acmt.003 - add the element ‘Know Your Customer Database Check’ to ‘Investor Profile Validation ‘ sequence. | JEC | By 20 May 2015 | CLOSED
4 | Statements | SEMT | Create the semt.002 Findel MP into v08 of the base standard | JEC | Autumn Global meeting | CLOSED |  | This action has been superseded with more recent work. See item 2015-10 Statements
2014-5 | Statements | semt | A change request is to created and submitted to ISO to request that semt.002.001.02 is dropped from the funds message set and semt.002.001.08 (or the later version if the standard is updated by S & R) would then be published with the funds message set (?). |  |  |  |  | not yet
6 | Orders MP on MyStandards | SETR | Upload to MyStandards and set to public | JEC | Q2 2015 | CLOSED | 21 April 2015 | SMPG-Global-IF-OrderProcessing-Final (2015-04-20)
7 | Orders | SETR | ‘Mutual Hedge Task Force’ – send invitation letter and date of first meeting to the ‘group’. | CB/JEC | Work starts May 2015 | CLOSED |  | Workshop took place at RBC, LU, 26 May 2015. Outcome seemed to favour updating mutual with hedge funds, rather than adopted hedge funds messages for mutual. This work has been superseded by GAIA initiative, which will be leverage to support the SWISS CR # 454
2014-8 | Data protection | GENL | Send question to S. Lindsay, Head of SWIFT Standards, - “Does SWIFT standards have to address data protection concerning private individuals’ this in the messages. If yes, how is it addressed?@ | JEC |  |  |  | New regulation on data privacy coming up. Does SWIFT have policy about data privacy? Is there any thought of indicator in message to indicate that sender is only passing on data or otherwise.
2014-9 | Corporate Actions | CA | Contact Sondra for a US contact for US input. Explain the colour conventions used in the spreadsheet before sending to CA. Discrepancy between event type DECR between FR and CBL- send e-mail to V. Vaudel requesting feedback. | CB
2014-10 | Corporate Actions | CA | Follow up on XS ISINs | TB |  |  | 20 November 2015 | Send the information (next column) to Christine Strandberg in follow-up. In context funds ICSD is simply a fund platform. | Short answer: everything is applicable (or at least theoretically possible) of the event types already shown as applicable for funds in Clearstream. It would be pointless to add a new column to our spreadsheet. Slightly longer answer: "XS ISINs" refers only to Eurobonds, and in this group there is actually a small number of "hybrid funds" issued as debt by MAN I.P. However, the ICSD environment doesn't only consist of XS ISINs, but we also have equities, warrants, etc, including funds, with safekeeping in the so-called common depositories. These depositories are designated as "common" because they provide shared safekeeping services for Euroclear and Clearstream, with daily netting procedures used in place of any bridge realignment. There are several common depositories, and they safekeep ISINs belonging to several national jurisdictions like LU, GB and IE in addition to the international XS.
11 | Transfers | SESE | No specific actions for SMPG at present. Rainer Vogelgesang to be invited to next Findel SLT meeting. | CB | May/June 2015 | CLOSED | 27 May 2015
12 | Autumn 2015 global meeting | GENL | Final confirmation of attendance in SG (for May meeting) | All |  | CLOSED | 23 June 2016
13 | Monthly Meeting Time | GENL | Cancel outstanding 2015 monthly meeting calendar note. Send new calendar note for the revised time. | JEC | End April 2015 | CLOSED
14 | Autumn 2015 global meeting | GENL | Put ‘Autumn Meeting finalisation’ on agenda for 19 May monthly meeting. Final decision on option (1) verses (3) to be agreed. See section 3. | JEC/CB ALL | 1st week May 2015 9 May 2015 | CLOSED
15 | Refresher on how to create collection using an SMPG collection as a basis | MyStds | Schedule for a monthly meeting | JEC | June 2015 monthly meeting. Covered in Oct SG meeting | CLOSED
16 | MP on BAH | BAH | Schedule for one of the next monthly meetings. JEC to prepare material. | JEC | June / Sept 2015 monthly meeting. Prepared for Oct SG meeting | CLOSED
17 | Global Meeting Country Reports | GENL | Produce a template for the country reports | CB | September 2015 | CLOSED
18 | RMG extension of membership | GENL | General follow-up | RV | Ad-hoc | CLOSED |  | type of membership. Is it beneficial if smpg join RMG.
19 | Corporate Actions (from 2014) | CA | DRIP, DVOP & DVSE definitions. Send an e-mail to J. Littre re semantic differences in definitions, raise change request. | JEC | October 2014 | CLOSED | 27 October 2014 | 19 March 2015 DONE (again)
2014-20 | MyStandards (from 2014) | MyStds | Create ‘tutorial’ power point describing best ways to search for a MP. | JEC | q2 2017
21 | MyStandards (from 2014) | MyStds | Report on status of outstanding functional improvements. | JEC | End Dec 2014 | CLOSED
22 | Corporate actions | CA | Create document describing funds specificities, post on MyStandards. | NM JEC | Spring 2015 meeting | CLOSED |  | SMPG-IFWG-CorporateActions_Recommendations.
Items added after SG SMPG meeting October 2015
2015-1 | Maintenance 2015-2016 | Maint 2016 | [1] Financial Instrument / Short Name check the definition [2] For the new Additional Information / Regulator element, an LEI format is NOT required | JEC | End October 2015 | CLOSED
2015-2 | ‘Maintenance 2017’ | Maint 2017 | Write a paper defining the scope of the maintenance proposal for submission to the Funds Migration Advisory Group (FMAG) for input and agreement. Will also be circulated to all NMPG countries and main users of the bulk messages for feedback. | JEC / CB / NM | End October 2015 | CLOSED | Q4 2014 | 30 October 2015: SMPG IF Conference Call. 4 November 2015 - revised document circulated to NMPG. 13 Nov 2015 - CB, NM, JEC conference call for next steps. Covering e-mail for SEG and FAG deliveries created. 19 Nov 2015: e-mail sent to chairman of FAG request FAG meeting | FAG = Funds Advisory Group
2015-3 | ‘Maintenance 2017’ | Maint 2017 | Decision on whether order maintenance for SR 2017 is to go ahead. | JEC / CB / NM | Mid December 2015 | CLOSED | Q4 2014
2015-4 | ‘Maintenance 2017’ | Maint 2017 | If the decision is ‘yes’ for order maintenance for SR 2017, then prepare a communication to SWIFT users of the order MXs. | JEC | Early January 2015 (or sooner) | CLOSED
2015-5 | Hedge / Alternative Funds | Maint 2017 | Analyse the GAIA market practice to determine work-arounds that should be eliminated with specific fields. To be used as input to change request 454 submitted by Switzerland. | JEC / TB | End December 2015 / January 2016 | CLOSED | Q1 2016 | JEC to attend GAIA meeting 20 November 2015
2015-6 | BAH – Helsinki Meeting | GENL | Request that the preliminary BAH MP is presented at the general session of the Helsinki meeting. | CB / NM / JEC | October 2015 | DEFERRED |  | E-mail sent to JL 14 October 2015 . Once Funds decide the BAH activation date then present to global group a year before.
2015-7 | Helsinki Meeting | GENL | Assess feasibility of funds starting the meeting the day before; request room. | JEC | November 2015 | CLOSED |  | 10 people can make it for a 1pm start.
2015-R | Helsinki Meeting | GENL | Request room for afternoon of 19 April. | JEC | End December 2015 | CLOSED | 6 Nov 2015 | E-mail sent 6 Nov 2017 to sari.rask@nordea.com
2015-8 | BAH | BAH | Create a collection that defines the MP as agreed in the Singapore meeting. Post on MyStandards. | JEC | End January 2016 | CLOSED |  | SMPG-Global-IF-BAH-Draft (2015-11-06)
2015-9 | BAH MP on MyStandards | BAH | Add to monthly meeting agenda for review by the group |  |  | CLOSED |  | To be discussed for next maintenance.
2015-10 | Statements | SEMT | Create a consolidated collection that contains usage guidelines for version 2 and version 8 of the messages, update the process document and post on MyStandards. | JEC | Helsinki | CLOSED | 20 November 2015 | SMPG-Global-IF-Statements-CONSOLIDATED-Draft (2015-11-20)
2015-11 | Transparency Report semt.041 | SEMT | Create a typical statement of holdings using semt.041 as a starting point for understanding the functionality of the transparency message. | JEC | For the Helsinki Meeting | CLOSED |  | Should not use semt.041 when a semt.002 is appropriate.
2015-12 | Transfers | SESE | Become familiar with the Findel SLT ‘simple’ market practice. | ALL | Helsinki | CLOSED |  | ALMUS FINDEL-LU-IF-SLT-AssetTransferProcessSimple - Final (24 April 2014) | A new item related to this was opened Sept 2016.
2015-13 | Orders MP | SETR | Add the recommendation about upper and lower case and character set to the orders process document, that is, references are NOT case sensitive. | JEC | End Dec 2016 | WIP |  | To be added in the order process document created for the update for SR 2017.
2015-14 | Account Management MP | ACMT | Migrate UG to new version of messages, upload to MyStandards and update of ‘process’ document with additional guidelines. | JEC | End January 2016 | CLOSED
2015-15 | Account Management MP | ACMT | Initial review of the new version of UGs and ‘process document. Then circulate to the wider group. | AM / SB, NH | Early February 2016 | CLOSED
2015-16 | Account Management MP | ACMT | Review and sign off new version. | ALL | Monthly meeting March 2016 |  |  | REQUEST THE OKAY FOR OCTOBER CALL.
2015-17 | MyStandards SMPG IF Group | GENL | Insert new SMPG logo. Write description of the group for the home-page. | JEC | End 2015 | CLOSED
Items added after Helsinki SMPG meeting April 2016
2016-01 | Statement of transactions | SEMT | Decide if the SEMT 006 can be replace by the generic statement SEMT017. | ALL | May 2016 conf call | CLOSED | Sept 2016 | This was discussed in the Zurich meeting. A new item related to this was opened Sept 2016.
2016-02 | Transfer | sese | Check the feasibility in the complex scenario that the client of the TA on the receiving side can send a SESE 005 to the transferor bank. | NM, All | May 2016 conf call
2016-03 | Maintenance | setr | Check how we can use supplementary data in case of unexpected change between two maintenance cycles | JEC, CB, NM | May 2016 conf call | Ongoing |  | Can we use the Supplementary Data prior to received 'approval' fro the RA, in an emergency for example. Can the ISO process be changed/adjusted.
2016-04 | Maintenance | SETR | Check if CR027 is still relevant or not. | Ben Cocks | May 2016 conf call | CLOSED
2016-05 | Order messages process document | setr | Need to update the process document with the new scope (new sentence) | JEC | June 2016 conf call | WIP
2016-06 | Transparency of holdings | setr | Create a market practice for those new messages | TB, JEC | Spring 2017 checkpoint |  |  | Priority should be given to statement of holding and maybe statement of transaction.
2016-07 | KYD (know your distributor) initiative by EFAMA/ICI |  | Jon to review the documentations for future messages needs | JW | Spring 2017 |  |  | MIFID related
2016-08 | Account management | ACMT | Need to review CR504 and the code list for the cash account. | All | June 2016 conf call | CLOSED
2016-09 | NMPG Update |  | Ask IE to have a NMPG update and their views on transfers | Nicola xxx | April 29th 2016 | CLOSED
2016-10 | Mission statement for the working group |  | Need to check if there is a document that defines the scope of the work of the investment funds. | Charles + Nadine + jec | Spring 2017 checkpoint | CLOSED | Sept 2016 | Question should be raised to David B and / or Omar R. The SETR process There will be a discussion with GAIA related to this.
2016-11 | Version and implementation strategy of ISO20022 |  | Need to discuss the problematics about the versioning, variances and implementation of the ISO20022 messages | ALL | June 2016 conf call | CLOSED | Sept 2016 | Presentation E. Piron (SWIFT in Zurich).
2016-12 | Maintenance | SETR | Need to inform SWIFT (Karen and Valerie) that SMPG is recommending to postpone the migration of the BAH to a later stage as it should be applied to all the investment funds message, not only the SETR. | Nadine + Charles | End of April 2016 | CLOSED | Sept 2016 | It has been agreed that BAH is not in scope of SR2017.
Items added after Zurich SMPG meeting September 2016
2016-13 | SMPG IF WG Co-chair | GENL | Consider standing for co-chair position, send 'letter of application'. | Any one
2016-14 | ISO 20022 Harmonisation Charter | GENL | Suggest the harmonisation presentation includes something about use of supplementary data to bridge the gap between two maintenance cycles - would be good for people to know this if a maintenance is skipped and change requests 'bundled'. | JEC | 26 Sept 2016 |  |  | E-mail to be sent to E. Piron (SWIFT)
2016-15 | ISO 20022 Harmonisation Charter | GENL | Harmonisation Charter decision to be made. (The decision was to support the charter.) | JEC | by 23 Sept 2016 | CLOSED | 23 Sept 2016
2016-16 | ISO process | GENL | Inform SEGS IF ET convenor of need to have better visibility on the supplementary data components used - ask for it to be followed-up.
2016-17 | Statements | semt | Finalise current MP collection - update semt.002.001.08 to semt.002.001.09 in preparation for Spring 2017 meeting, request group to set collection to public. | JEC | Spring 2017 meeting
2016-18 | Statement of Investment Funds Transactions semt.006 | semt | Send e-mail to S & R SMPG about viability of adding transaction overhead and related parties to semt.017 | JEC NM CB |  |  |  | We need to convince S & R that funds should converge with Securities and drop semt.006
2016-19 | Securities Transaction Posting Report semt.041 | semt | Review message usage and examples documented in UHB as precursor to MP work. | TB | For Spring meeting
2016-20 | Account Management 2016 | acmt | 2016 Version - market practice collection for Nov 2016 version of standard needs to be approved and set to 'public' | JEC |  |  |  | This should have been set to public after the Helsinki meeting. JEC is to pursue, try to get it signed off in a monthly meeting.
2016-21 | Account Closure 2017 version | acmt | E-mail: to Teemu, NM JEC conf call -ask preference re closure via 003 or new message. | JEC | 26 Sept 2016
2016-22 | Account Management 2017 version | acmt | 2017 version: process document update it to include message flow for closure | JEC | January 2017 |  |  | Norway and Italy strongly suggest this.
2016-23 | Account Management 2017 version | acmt | 2017 version: migrate usage guidelines from 2016 to 2017 | JEC | January 2017
2016-24 | Account Management 2017 version | acmt | 2017 version: review meeting JEC, Norway, Italy, Denmark | JEC | January 2017
2016-25 | Account Management 2017 version | acmt | 2017 version: review by larger SMPG group, final modifications and final publication on MyStandards |  | Monthly meeting or Spring meeting
2016-26 | Orders | setr | Onshore/Offshore - Send e-mail to KY, HK re results of discussion | JEC
2016-27 | Orders | setr | Onshore/Offshore market practice one - pager. | JEC, JW
2016-28 | Orders | setr | Process document: add item for 'references are not case sensitive'. | JEC | by Nov 2016 monthly
2016-29 | Orders | setr | Update order process document | ALL, JEC | by Nov 2016 monthly | WIP |  | Work started in Zurich meeting. JEC to update the XML examples, provide more XML examples,
2016-30 | Orders | setr | Migrate order MXs usage guidelines | JEC | by mid-January 2017
2016-31 | Orders | setr | Coordinate additional physical meeting Feb 27 & 28 | TB, JEC | by Oct 2016
2016-32 | Orders | setr | Prepare for February meeting by reviewing the new message usage guidelines | ALL | by 27 February 2017
2016-33 | Orders | setr | GAIA - organise conf call NM, CB, TB, Bill Gourley, Steve W | JEC | by November 2016 |  |  | SMPG IF needs to work out how to integrate hedge/alternative funds MP
2016-34 | Orders | setr | Publish '2017' version of the market practice on MyStandards 'public' |  | by April 2017
2016-35 | Orders | setr | MiFID II and its impact of the investment fund message set - initial review. Jon Willis (and Andrea) to provide an updated | JW | Spring 2017 meeting
2016-36 | Simple SLT | sese | Review the Findel simple SLT process document. Add to the document information that sets the context, defines the scope of its usage, the constraints - see Zurich minutes section 23. | JEC | by end of September 2016 |  |  | JEC initiate the action, consult with RV
2016-37 | Simple SLT | sese | Review the usage guidelines for Findel simple SLT process in preparation for the Spring meeting | All | Spring 2017 meeting
2016-38 | Simple SLT | sese | Migrate the usage guidelines for Findel simple SLT process and upload to MyStandards in preparation for the Spring meeting | JEC | Spring 2017 meeting
2016-39 | Simple/complex SLT | sese | Draft statement of SLT issue --> RS to ask EFAMA, etc | TB, JW | End 2016 | WIP
2016-40 | Complex SLT | sese | Make complex Findel usage guidelines accessible to SMPG
2016-41 | Double leg | sese | Double leg process - get started. | TB, JW | Spring 2017 meeting
2016-42 | ISO 20022 documentation clarity | GENL | ISO 20022 Document Clarity provided by RV, circulate and put on agenda for conference call. | JEC
2016-43 | Housekeeping | GENL | JEC schedule the monthly calls for next 6 months. | JEC
2016-44 | Housekeeping | GENL | 2017 SIBOS is in Toronto, it is expected that SMPG will also be in Toronto. Make decision on whether Toronto can be the venue for Funds WG or whether we need separate meeting and therefore a host to step forward. | JEC | October monthly meeting
Note on E53: Charles Boniver: the submitter of the CR