## Global MP
17
Market Practice | New Business Template | ISO20022 Illustrations | Owner | Due Date | Done
Sell Buy - Buy Sell Back v 6_0 | Y | N | Evelyne | 2016-09-01 | On hold missing codes in sese.033
Auto Registration Reporting | Y | Y | Evelyne | 2016-03-01 | ON MS
Bilateral Collateral | Y | N | Evelyne | 2016-09-01 | DRAFT illu in MP
Block_Bulk Trade Settlement | Y | Y | Evelyne | 2016-03-01 | ON MS
Book Transfer | Y | Y | Evelyne | 2016-03-01 | ON MS
Cash Securities Split Settlement | Y | Y | Alex | 2016-03-01 | ON MS
Depositary Receipts | Y | N | Cindy | 2016-09-01 | Illustration in doc
Factored Securities | Y | N | Evelyne | 2016-09-01 | DRAFT illu in MP
Financial Instrument Identification | Y | To be included in Common Elements MP | Evelyne | 2016-03-01 | Included in Common Elements MP
Function of Message | N/A | N/A
FX order And Confirmation | Y | N/A
Global Time Deposit | Y | N/A
Hold And Release | Y | N | Marcin | 2016-09-01 | Illustration in doc
IPO | Y | N/A?
Linkages | Y | N | Evelyne (doc to be attached to Common elements MP) | 2016-09-01 | The PDF of the MP has been uploaded in MS
Listed Derivatives Trade Notification And Management | Y | N | Karine | 2016-09-01
Balance Custody And Accounting Report | Y | Y | Karine | 2016-03-01 | ON MS
Securities Settlement Transaction Posting Report | Y | Y | Karine | 2016-03-01 | ON MS
MT 548 MT537 | N | N | Karine | 2016-09-01
Pair off | Y | Y | Karine | 2016-03-01 | ON MS
Partial Settlement | Y | Y | Alex | 2016-03-01 | ON MS
Physical Settlement | Y | Y | Alex | 2016-03-01 | ON MS
Receiving Delivering Depository - PSET PSAF | Y | Y | Karine | 2016-03-01 | ON MS
Repo | N | N | Karine | 2016-09-01
Securities Settlement Transaction Pending Report | Y | Y | Evelyne | 2016-03-01 | ON MS
Securities Settlement Allegment | Y | Y | Alex | 2016-03-01 | ON MS
Securities Lending and Borrowing | Y | N | Robin | 2016-09-01 | Illustration in doc
Securities Settlement _ Modification | Y | Only in 20022 | Karine | 2016-03-01 | ON MS
Common Elements | Y | Y (to be approved by SMPG) | Evelyne | 2016-03-01 | ON MS
Split Settlement | Y | Y | Evelyne | 2016-03-01 | ON MS
Third Party Foreign Exchange | Y | N/A
Transaction Processing Command | Y | N | Marcin | 2016-09-01 | Illustration in doc

## Local MP
Country | Market Practice on SMPG Website | Market Practice on MyStandards | Aligned with Global MP
Australia and New Zealand | x
Austria | x
Belgium | x (Ref to ESES document)
Brazil | x
Canada | x
Denmark | x | x
ECSDA (Inter-CSD settlement) | x
Egypt | x
ESES | x
France | x (Ref to ESES document)
Grece | x
Germany | x
Hong Kong | x
Hungary | x
ICSD | x
India | x | x
Indonesia | x
Israel | x
Italy | x
Japan | x
Korea | x
Latin America | x
Luxembourg | x
Malaysia | x | x
Nordics | x
Poland | x
Portugal | x
Russia | x | x
Singapore | x | x
x
South Africa | x
SPAIN | x
Switzerland | x
Taiwan | x
The Netherlands | x (Ref to ESES document)
Turkey | x
UK Ireland | x | x
US | x