## Open Actions
Action Id | Description | Assigned to | Status | Creation date | Last change | Comments
21-03 | UTI as a common transaction identifier to be utilised by SWIFT E2E transaction tracker. | Charifa/ All | Open | 2021-02-16 | 2022-06-15 | 2021-02-16 - presentation by Lotte Laursen and initial discussion 2021-03-16 - discussion continued: - UTI vs other available identifiers - UTI seems to be the best one; - Analogy to gpi, but securities business is not the same; - Using existing field TRRF vs creation of new one; - ISO20022 solution; - Business case not always clear; - Complex scenarios to be examined, including allocations, splits, netting, partial settlement, instructions created by MIs. 2021-04-15 - discussion with Charifa. Further steps to be decided based on input from SWIFT working group to be provided in following weeks. 2021-06-15 - update presented by Didier Hermans followed by discussion. SMPG to coordinate identification, review and updates to consider Unique Transaction Identifier (UTI) 2021-10-08 - Robin nominated as SMPG representative to UTI expert group. SMPG to follow the project and provide neccessery assistance related to global MPs. Between October 2021 and May 2022 updates were presented by Charifa followed by discussions during monthly calls 2022-06-15 - update provided by Simon Daniel
21-07 | Settlement MP summary matrix - need for update | Jason, Robin, co-chairs | Open | 2021-03-04 | 2021-10-04 | 2021-04-16 - need for update confirmed. SMPG participants asked to review and provide comments. Co-chairs to schedule discussion. 2021-07-14 - Document updated: party identifiers in ESES markets. 2021-10-04 - Item open for further review by SMPG members. 2022-10-10 - Item closed, as each market representative owns the document. Document available under global MPs too now
21-11 | Hold -Release MP - review and track SR2022 Change Request for status message advice | Ton/Arnaud | Open | 2021-04-13 | 2021-10-05 | 2021-10-05 - additional updates and illustration related to SR2021 to be provided by Ton 2022-09-01 Arnaud provided examples of SR changes to consider, MP to be updated 2022-10-10 Discussed updated language, Arnaud to update and distribute for review | X
21-15 | CSDR penalties MP - pagination rules | Aranud/ Robin | Open | 2021-10-04 | 2022-05-05 | 2021-10-04 The recommendation was to include a paragraph or comment within the market practice document concerning reccomended pagination rules. 2022-05-05 - Robin to submit CR for SR 2023 in order to provide easier and consistent pagination mechanism 2022-09-30 - CR submitted for SR 2023, accepted through maintenance, out for country vote | X
21-16 | CSDR penalties MP - penalty reference in MT940/ 950 cash statement message | Robin/ Charles | Open | 2021-10-04 | 2022-05-05 | 2021-10-04 Robin will engage with Charles to discuss approach 2022-05-05 Charles informed about Payment Taskforce activities. PEN code is used in MT payment statements. A proper 4 character code will be agreed for ISO20022 in June. The penalty MP should be updated after the new code has been finalised.
21-17 | MP summary list - refine and distribute the document | Aundie | Open | 2021-10-05 | 2022-06-15 | 2021-10-05 Aundie to finalize market practice summary document descriptions, tiered priorities, and distribute to working group members The discussion will continue at the next physical meeting 2022-6-15 Update reviewed at June session, document distributed for review and volunteers for market practice updates 2022-10-10 Market practice ownership updated with exception of Listed Derivatives, pending stats from Alexandre. Document to be distributed as part of conference materials.
21-18 | MP maintenance process | Aundie | Open | 2021-10-05 | 2022-06-15 | 2021-10-05 Aundie to contact local market practice contacts to confirm relevance and recommendation to review and update within +5 years. The discussion will continue at the next physical meeting 2022-06-15 Documentation and practice reviewed at June session. Create summary document of market practice issues and proposals for Market Practice review process completed. Contact with local market representatives deferred until bylaws and practice finalized
21-19 | MyStandards UG migration to the next SR | co-chairs, all | Open | 2021-10-08 | 2021-10-08 | 2021-10-08 to finalize approach to determine how SMPG group will we handle the next migration. The discussion will continue at the next physical meeting 2022-06-15 discussed utility button is not available until end of 2023. Comparison exists within UG 2022-10-10 SWIFT to own process until utility button made available
21-20 | Recommendation on quantity and amount values exceeding respective field definition | Arnaud/ Marcin | Open | 2021-10-08 | 2022-04-07 | 2021-10-08 Arnaud volunteered to provide documented background summary and proposed solutions for further discussion of field length limitations 2022-04-07 Following previous discussions Marcin prepared draft of the guideline document provinding information on long quantity/amount fields. Discussion to be continued.
22-01 | AMI-SeCo - harmonisation workgroup for settlement messages in ISO20022 | Annemie, all | Open | 2022-01-13 | 2022-01-13 | 2022-01-13 AMI-SeCo with relation to its ECMS system recognises the need of harmonised use of ISO standards not only for CA, but also in S&R space. AMI-SeCo is looking into possiblity of working together with SMPG on some recommendations.
22-02 | Digital assets processing | David/Alexandre | Open | 2022-05-05 | 2022-05-05 | 2022-05-05 David presented key isssues related to processing digital assets with MT messaging. David to submit CR on behalf of SMPG, but limited only to change the usage rule on safekeeping account. 2022-09-01 Alexandre provided an update of the maintenance review, all accepted, out for country vote
22-03 | Set of SR2023 CR's | Robin | Open | 2022-05-05 | 2022-06-15 | 2022-05-05 Robin to submit CRs on behalf of SMPG: - continuation flag in penalties reporting; - PSTA usage for penalties reporting; - additional sub-balance codes in MT535; - clarification on SEME use in statements. 2022-06-15 CR update from Alexandre at June session, reviewed submissions 2022-09-01 Alexandre provided an update of the maintenance review, all accepted, out for country vote
22-05 | SMPG user activity to access or review SnR market practice documents | Alexandre | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Alexandre to provide statistics on the frequent and user activity for SnR MP on smpg.info reviewed by the community
22-06 | Remove invalid local market practice documents from SMPG site | Alexandre | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Alexandre to remove the Spanish market practice document, on the local market practice page as the document does not cover the T2S migration, and other infrastructure changes in the market are not accurate. 2022-10-10 Item to be closed
22-08 | CSDR Buy-in MP | Annemie | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Annemie to update the CSDR buy-in market practice document/cover to highlight future implementation date based on regulatory outcomes postponed until 2025.
22-09 | CSDR penalties MP - removal of cash penalty | Arnaud | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Arnaud to review history on language in the MP and provide recommended language change
22-10 | CSDR penalties MP - update to cash penalty | Christine | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Christine to provide a drafted statement for the MP update to clarify update to a cash penalty
22-11 | CSDR penalties MP - clarify switch and realloaction for cash penalty | Christine | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Christine to provide a drafted statement for the MP update to clarify reallocation/switch/removal
22-12 | CSDR penalties MP - netting penalties | Robin | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Custodian may want to offer a service to net debit/credits. The option and proposal to net is not documented and should be assessed.
22-13 | CSDR penalties MP - unique reference identifiers | Arnaud | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Arnaud to draft a recommendation for reference identifiers with the penalty reports. ISO has two separate fields between statement message reference and the unique reference id. 2022-10-10 Options reviewed at conference, still under review
22-14 | CSDR - linked trades | Marcin | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Marcin to define the process for the linking and market workflow. This may also be an action item to confirm with ESMA once the discovery of the topic is complete. Ton shared the minutes from the T2S review of Iberclear request related to linked trades. 2022-10-10 To be closed
22-15 | SMPG bylaws updates | Armin | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Armin to draft changes to the by-laws specific to NMPG role and responsibilities. 2022-08-09 Group reviewed draft and provided feedback, to be presented in October 2022-10-10 Group reviewed draft, next version to be distributed for comments | x
22-17 | Market practice approvals - Time Deposits | Aundie/Robin | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Demand to revisit Time Deposit published market practice. Need to identify SMEs to reassess open questions on rollover complex interest vs. compounding scenarios
22-18 | Documentation management for SnR internal documentation | Mihaela/Alexandre | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Mihaela to follow with Alexandre on the approach for documentation sharing on MyStandards for private SMPG group. 2022-10-10 Group decision on approach, Alexandre to create landing page on smpg.info and post document with internal password | x
22-19 | FED CAP MT535 question on rehypothecation | David | Open | 2022-10-10 | 2022-10-10 | 2022-10-10 David to document the full business case to review the condition and make a decision on best practice and whether to include for an SR2024 change request.
22-20 | Recommendation on elements for securities transactions in CAMT.053 | Denis | Open | 2022-10-10 | 2022-10-10 | 2022-10-10 Denis to summarize the recommended data elements to include in CAMT.053, SnR working group to review, including Charles Boniver
22-21 | SMPG.Info modification date not posted | Alexandre | Open | 2022-10-10 | 2022-10-10 | 2022-10-10 Alexandre to review with SWIFT why the modification date is not reported on the SMPG.info landing page of the market practice document links.
22-22 | Table of contents for market practice documetns | Aundie | Open | 2022-10-10 | 2022-10-10 | 2022-10-10 Aundie to create a summary document / table of contents for the settlements MP documents
22-23 | SMPG market practice documents to include ISO 20022 payment messaging | Aundie | Open | 2022-10-10 | 2022-10-10 | 2022-10-10 Aundie partner with Dean Chard to review SMPG market practice documents to include translation of cash examples for ISO 20022 payments messaging.
22-24 | Status Advice Codes Grid review | Suzanne | Open | 2022-10-10 | 2022-10-10 | 2022-10-10 Suzanne will coordinate further reviews and share drafted market practice language with the working group, as it relates to the grid on page 10 of Status Advice MP
22-25 | Digital assets working group representation | All | Open | 2022-10-10 | 2022-10-10 | 2022-10-10 Assess SME participants and attendees in Settlements & Reconciliation WKG necessary to progress digital assets
22-26 | CSDR penalties MP - internalized settlement | Arnaud | Open | 2022-10-10 | 2022-10-10 | 2022-10-10 Arnaud to update language in market practice document to highlight that internalized settlement will likely result in no penalties reporting.
22-27 | Meeting attendance | Alexandre | Open | 2022-10-10 | 2022-10-10 | 2022-10-10 Alexandre to add Paoula to the invites for the ECSDA framework view in our working group focused on CSDR
22-28 | CSDR penalties MP - DACO | Arnaud | Open | 2022-10-10 | 2022-10-10 | 2022-10-10 Arnaud add comment on DACO

## Closed
Action Id | Description | Assigned to | Status | Creation date | Closing date | Comments
20-01 | Organise Webex working call on March 31st 14:00 CET | Alex, Paul | Done | 2020-03-10 | 2020-03
20-02 | Update MP spreadsheet with the new owner details and distribute it to the members | Marcin | Done | 2020-03-10 | 2020-03
20-03 | Make MS Word version of MP documents available to SMPG members | Alex | Done | 2020-03-10 | 2020-03
20-04 | Update the presentation based on SMPG comments | Arnaud | Done | 2020-03-10 | 2020-03
20-05 | Convert provided presentation into SMPG MP document. | Aranud | Done | 2020-03-10 | 2020-03
20-06 | Provide ISO20022 illustration (semt.044). | Annemie | Done | 2020-03-10 | 2020-03
20-07 | Go back to the Danish community to discuss the SMPG feedback | Suzanne | Done | 2020-03-11 | 2020-03
20-08 | prepare feedback regarding settlement status for unmatched instructions for the next working call. | All | Done | 2020-03-11 | 2020-03
20-09 | prepare a draft of CR to clarify CYCL usage | Robin | Done | 2020-03-11 | 2020-03
20-10 | Updated MP will be shared with participants | Ton | Done | 2020-03-11 | 2020-03
20-11 | Depending on the results of the working call, there may be a need to prepare a CR. | Robin | Done | 2020-03-11 | 2020-03
20-12 | SMPG to prepare an official reminder on settlement transactions codes |  | Closed | 2020-03-11 | 2020-10 | 29.09.2020 - No SMPG role
20-13 | updated presentation, with the timeline of the process added, will be shared with participants. | Paul | Done | 2020-03-12 | 2020-03
20-14 | prepare a draft MP on CSDR buy-ins | Annemie, Arnaud | Done | 2020-03-12 | 2020-03
20-15 | prepare a CR draft related to buy-in status advise. | Robin | Done | 2020-03-12 | 2020-03
20-16 | prepare a CR draft related to internal settlement advise | Robin | Done | 2020-03-12 | 2020-03
20-17 | Prepare for discussion on partial settlement eligibility reporting for the next working call. | Arnaud/ Alberto/ All | Done | 2020-03-12 | 2020-03 | 2020-10-28 - business case to be refined. Various opinions within the group. Discussion to be continued in November 2020-11-17 - Alberto to provide T2S and their customers feedback on partial settlement eligibility status reporting for December 2020 call 2020-12-15 - Alberto confirmed, based on T2S Regulatory Task Force opinion, that there is no regulatory requirement to provide value of counterparty partial settlement indicator. There are several ways to inform about partial settlement – including GUI. With lack of a clear business case and no common view on the possible solution, SMPG decided to close the topic.
20-18 | Assign numbers to the existing and new actions | Marcin | Done | 2020-09-28 | 2020-10
20-19 | Prepare document containing summary of the actions | Marcin | Done | 2020-09-28 | 2020-10
20-22 | Prepare a summary of the differences between SMPG MP and T2S solution (done before the minutes were distributed); | Ton | Done | 2020-10-01 | 2020-10
20-27 | Provide comments to the MP names proposed in the MP summary spreadsheet | all | Closed | 2020-10-02 | 2020-11 | Deadline for comments was Oct 16th 2020. Names approved with no coments received.
20-33 | Send invitations to working calls | Alex | done | 2020-10-02 | 2020-10
20-21 | Share non-confidential information of the APAC API working group with SMPG | Cindi/ Alex | Closed | 2020-09-29 | 2021-04-15 | 2021-04-15 Presentation on ISO20022 based API development process provided by Tom Alaerts, Neil Munro and Tapas Bhattacharya
20-24 | Organise a session with SWIFT IT API expert to discuss the technical details of API development including standards implications. | Alex | Done | 2020-10-01 | 2021-04-15 | 2021-04-15 Presentation on ISO20022 based API development process provided by Tom Alaerts, Neil Munro and Tapas Bhattacharya
20-26 | Provide the group with progress update and share the experience of the UG migration | Alex/ SWIFT | Done | 2020-10-02 | 2021-04-13 | 2021-04-15 Presentation on ISO20022 based API development process provided by Tom Alaerts, Neil Munro and Tapas Bhattacharya
20-31 | Provide updated Securities Transaction Posting Report MP and Allegement MP; | Suzanne | Done | 2020-10-02 | 2021-04-13 | 2021-01-06 Suzanne provided updated Securities Transaction Posting Report MP and Allegement MP to be reviewed by SMPG members by the end of January 2021-04-13 - Updated version presented and approved
20-32 | Provide updated Function of the Message MP. | Marcin | Done | 2020-10-02 | 2021-04-13 | 2021-04-13 - Updated verison presented and approved
20-35 | Update Partial Settlelent MP to clarify usage of quantity and amount in cancellation instructions | Aundrea | Done | 2020-11-17 | 2021-04-16 | 2020-11-17 - Aundrea agreed to provide update to MP before December conf call 2020-12-15 - updates provided by Aundrea Changes in Partial Settlement MP has been approved. Word ‘effectife’ to be removed in amount definiton. Aundrea will update T2S section explaining full amount/quantity rule. There shouild be a link in Partial Settlement MP to FX MP, but it will be done later, after FX MP update. 2020-12-18 - new version provided by Aundrea 2021-01-12 - additional comments provided 2021-02-16 - decided to finalise the discussion during global meeting in April 2021-04-16 -new version presented by Aundrea unanimously approved .
21-01 | Penalty reporting for market claims | Arnaud | Done | 2021-01-12 | 2021-03-16 | 2021-01-12 - initial discussion basd on presentation provided by Arnaud 2021-02-16 - further discussion 2021-03-16 - using Corporate Actions reference, underlying instruction reference and CLAI transaction type would be an ideal solution in penalty report. T2S - penalty report contain reference to underlying market claim. Status message of market claim contains reference to underlying instruction. Penalty report does not contain section for linkages. Difference between market claims nad transformations were discussed. Specific market claims messages in iso20002 are created, but they are not implemented by anyone still. Automated and proper market claims reporting does not exists today.
21-02 | CSDR penalties MP update | Arnaud, Alberto | Done | 2021-02-16 | 2021-04-12 | Updated document received from Arnaud on February 16th with Alberto comments received on February 25th. Safekeeping account moved to the top level of the semt.044. To be approved during April meeting. 2021-04-12 - latest updates discussed and approved
21-04 | CSDR penalties global testing | Jason | Closed | 2021-01-27 | 2021-04-12 | 2021-04-12 - T2S 'dry run' schedule discussed. Other institutions should follow simmilar pattern, but it is impossible to enforce it globally.
21-05 | CSDR penalties - Transaction reference information in the monthly reports | Sari | Closed | 2021-02-23 | 2021-04-12 | Reference information recommended in SMPG MP
21-06 | CSDR penalties - Payment date | Sari | Closed | 2021-03-02 | 2021-04-12 | Payment date recommended in SMPG MP
21-08 | BSSP and BPSS codes | Arnaud | Done | 2021-03-16 | 2021-04-16 | 2021-03-16 - BPSS is the standard solution as of SR2021; - BPSS will be implemented by T2S, but later than Feb 2022; - BSSP and BPSS will have to co-exist for a time being; - Arnaud to approach ECSDA about the issue. 2021-03-16 ECSDA advising support for both solutions
21-09 | Field BENE//4!c in MT578 and MT586 in the context of CSDR SDR | Arnaud | Closed | 2021-03-11 | 2021-04-16 | BENE field is otpional and no strong justification to make it mandatory.
20-23 | Update the Hold/release MP document for the next round of discussions | Ton | Done | 2020-10-01 | 2021-04-13 | 2020-11-17 Ton to provide updated version for the Junuary 2021 call 2021-04-13 - latest updates in the document presented and accepted
20-28 | Change the MP names on smpg.info website based on the spreadsheet | Alex | Done | 2020-10-02 | 2021-04-29
20-29 | Check the possibility of having additional attributes (e.g. message names) in the MP list on the website; | Alex | Closed | 2020-10-02 | 2021-10-04 | 2021-10-04 - Alex informed that additional functionalities of the website would require some investments that SMPG have no budget for. Current functionality agreed to be suffiecient.
20-30 | Update the MP spreadsheet to include description, message names etc | Aundrea/Marcin | Done | 2020-10-02 | 2021-10-05 | 2021-10-05 - Aundrea enriched the spreadsheet with additional attributes and content. Updated document was presented discussed with SMPG
20-34 | Approach ECSDA to provide more detailed guidelines, suggesting real-time reporting, not EOD. | Arnaud | Closed | 2020-10-28 | 2021-10-04 | 2020-10-29 - Cash reporting of CSDR penatlies distributions was discussed, including MT910 vs MT940/950 vs PFOD solution. Cash mesages out of S&R scope. On the other hand lack of a single and clear solution will casue issues (increased complexity and cost). 2021-04-12 - ECSDA postion to be confirmed 2021-10-04 - Arnaud confirmed the requirement was reflected in the new version of ECSDA guidelines.
20-36 | New FX reversal code related to partial settlement scenario | Robin | Deferred | 2020-12-15 | 2021-04-07 | 2020-12-15 - invited JPM representatives presented the need of having a new code for s scenario where the forex instructed in the original instruction is to be cancelled for the unsettled portion of the trade and not cancelled for the settled portion. It was agreed to use a new code - FXPA. As a temporary solution, the new code will be used with SMPG DSS. The final solution with a proper new code could be proposed as a regular CR for SR2022. Robin will update FX MP document accordingly. There will be a reference in Partial Settlement MP too. 2021-04-16 - Updated MP to be discussed in May 2021-10-07 - Impact of CSDR on FX reversals to be reasssed in April 2022 meeting. If needed CR will be resubmitted for SR2023.
21-12 | Making SAFE repetitive to reflect chains of safekeeping places | All | Closed | 2021-04-16 | 2021-10-04 | 2021-04-16 - two sessions with CA WG. Solid case presented for MT564. Business case for MT535 change to be further discussed within S&R WG. 2021-05-18 - Co-Chairs monitor response from CA working group on the progress of their assessment, and whether a CR will be submitted 2021-10-04 - Item closed until new requirements arise from CA WG
21-13 | MP maintenance spreadsheet -schedule discussion to review approach and content updates in more detail | co-chairs | Closed | 2021-04-16 | 2021-10-05 | 2021-10-04 - Aundrea conducted the discussion on new approach and schedule. Collective updates introduced as a way forward.
21-10 | Penalty reporting MP - review and coordinate feedback custodian to asset manager points to consider within the MP | Robin, Jason, Aundrea | Closed | 2021-04-12 | 2021-10-04 | 2021-10-04 - Items discussed several times during monthly calls. No furher requirements identified.
20-25 | Complete UG migration on MyStandards taking into account agreed priorities; | All | Closed | 2020-10-02 | 2021-10-08 | 2021-04-13 - Didier presented scope and progress of migration. Complete migration is expected by the end of April. 2021-10-08 - Migration completed to SR2021. Didier presented the outcome of the migration. It was decided that SMPG would collectively update MyStandards collections for the following SRs starting from April 2022 meeting.
20-20 | Contact Spanish NMPG representatives (S&R and CA) to discuss the possibility of updating the MP. If that’s unsuccessful, the MP will be marked as ‘obsolete’ in the SMPG repository. | Marcin/ Aundrea | Closed | 2020-09-29 | 2021-11-09 | Marcin asked to reach out to Spanish NMPG in order to get update. Spanish NMPG approached by Marcin in June and Aundrea in September. SMPG decided to mark MP as 'outdated' in SMPG repository until the documents gets updated.
21-14 | CSDR penalties MP - order of fields in a sequence | Arnaud | Closed | 2021-10-04 | 2022-10-05 | 2021-10-04 Arnaud will validate the MP document samples are in order and consider the order of a field in a sequence. 2022-05 - Arnaud provided updates to MP
22-16 | Market practice approvals - bi-lateral repos | Aundie | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Aundrea complete the market practice draft and finalization for four changes to the Bi-lateral Repo document completed by ISITC Settlements WKG. 2022-07-01 Update posted
22-04 | SR Maintenance process | Alexandre | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Alexandre to provide response on how T2S volume is contemplated within the maintenance working groups representation for volume. 2022-07-01 The volume of T2S is ISO20022 only and shared between countries.
22-07 | CSDR penalties - MT548 volumes | Alexandre | Open | 2022-06-15 | 2022-06-15 | 2022-06-15 Alexandre to provide general messaging volumes for penalties using MT548 across industry. A question was raised around continuing to reference mt548 for penalty related CRs and market practice updates. 2022-07-01 For March and April 2022 the usage was 41.323 MT548 Messages with the function PENA.